CORVUS

Mobile AR Tactical HUD

COMPLETE PROJECT PLAN  //  13-WEEK BUILD

Version 1.0  ·  Author: Nirmal  ·  Budget: ₹0  ·  License: MIT

| Field | Value |
| --- | --- |
| Project Code | CORVUS-01 |
| Start Date | Week 1, April 2026 |
| Target Launch | Week 13, July 2026 |
| Stack | Next.js 16.2.1 · TypeScript · TensorFlow.js · Tailwind v4 |
| Hosting | Vercel (free tier) |
| Budget | ₹0 — Zero paid APIs or services |
| Privacy Policy | Zero external data — all inference runs on-device |

# 01  EXECUTIVE SUMMARY

Corvus is a mobile web AR application that overlays a real-time heads-up display on the phone camera feed. Using only on-device machine learning (TensorFlow.js + COCO-SSD), it detects and labels objects in the environment and presents them in a tactical HUD aesthetic — angular panels, cyan-on-black palette, Orbitron typography.

The project has zero backend requirements for core functionality. A single Vercel Serverless Function (/api/jarvis) routes voice queries to Gemini 2.0 Flash-Lite for a conversational overlay. No user data, GPS coordinates, or camera frames are ever transmitted externally.

Corvus is a 13-week solo build structured across four phases — from a working camera-plus-detection MVP through to a fully polished PWA with Web Worker offloading.

## Key Goals

- Ship a working mobile web AR MVP by end of Phase 1 (Week 3)

- Achieve ≥10 FPS object detection on mid-range Android devices

- Maintain a ₹0 operational cost throughout the entire project

- Preserve strict on-device privacy — no raw frames or GPS leave the device

- Build a showcase-quality portfolio piece for Product Engineer / AI Product roles

## Success Metrics

| Metric | Target | Category |
| --- | --- | --- |
| Initial load time | < 5s on 3G | Performance |
| Detection FPS | >= 10 FPS sustained | Performance |
| JS heap usage | < 300 MB | Performance |
| Battery drain | < 10% per hour | Performance |
| Lighthouse score | >= 85 (mobile) | Quality |
| PWA installable | Yes (Phase 4) | Distribution |
| Build passing | All phases | Stability |

# 02  TECH STACK

All dependencies are pinned to exact versions from package.json. Do not upgrade without reviewing breaking changes — especially Zustand v5 (new create API) and Framer Motion v12 (dropped legacy variants API).

## Production Dependencies

| Package | Version | Role |
| --- | --- | --- |
| Next.js App Router | 16.2.1 | Framework |
| React / React DOM | 19.2.4 | UI Runtime |
| TypeScript | ^5 | Language |
| Tailwind CSS v4 | ^4.2.2 | Styling |
| @tailwindcss/postcss | ^4.2.2 | CSS Build |
| Framer Motion | ^12.38.0 | Animation |
| Zustand | ^5.0.12 | State Mgmt |
| TensorFlow.js | ^4.22.0 | ML Runtime |
| @tensorflow-models/coco-ssd | ^2.2.3 | Object Detection |
| Lucide React | ^1.7.0 | Icons |
| @google/generative-ai | ^0.24.1 | Gemini SDK (server-only) |

## Tailwind v4 — Critical Rules

- Theme tokens live in app/globals.css inside @theme {} — not a config file

- PostCSS plugin: @tailwindcss/postcss in postcss.config.mjs

- No tailwind.config.ts — that is a v3 pattern; do not create one

- No arbitrary values like bg-[#00D4FF] — use named tokens (bg-hud-cyan, etc.)

@theme { --color-hud-cyan: #00D4FF; --color-hud-dark: #0A0A0F; --color-hud-panel: rgba(0, 212, 255, 0.05); --color-hud-border: rgba(0, 212, 255, 0.3); --font-orbitron: 'Orbitron', monospace; --font-mono: 'Share Tech Mono', monospace; }

# 03  SYSTEM ARCHITECTURE

Corvus has a deliberately simple architecture. All heavy lifting — camera access, ML inference, geolocation — runs entirely in the browser. The only server-side component is the Gemini proxy route.

## Component Map

app/ layout.tsx Root layout: fonts, metadata, suppressHydrationWarning page.tsx Entry point: mounts <HUD /> over camera feed globals.css Tailwind v4 @theme, scanline overlay, keyframes api/ jarvis/route.ts Serverless fn: proxies voice query to Gemini components/ camera/ CameraFeed.tsx getUserMedia, video element, permission gate hud/ HUDShell.tsx Absolute-positioned overlay container TopLeftPanel.tsx Object count, FPS counter, scan status TopRightPanel.tsx Battery, time, location label (coords only) BottomBar.tsx Detected object list, Jarvis input CornerBrackets.tsx Reusable angular corner decoration detection/ BoundingBoxes.tsx SVG overlay: draws detection rectangles + labels overlays/ Scanlines.tsx CSS pseudo-element scanline effect AnimatedGrid.tsx Background tactical grid animation hooks/ useCamera.ts getUserMedia, stream management, ref useDetection.ts TF.js inference loop, FPS measurement useLocation.ts navigator.geolocation.watchPosition useLocalTime.ts Device clock, formatted display useBattery.ts navigator.getBattery() store/ hudStore.ts Zustand v5 store — all shared state lib/ constants.ts Colours, thresholds, config utils.ts formatCoords, formatFPS, clamp helpers workers/ (Phase 4) detection.worker.ts Web Worker: offloads TF.js from main thread

## Data Flow

| Data | Flow | Privacy |
| --- | --- | --- |
| Camera stream | getUserMedia → <video> | On-device only |
| Video frames | <video> → TF.js canvas → COCO-SSD inference | On-device only |
| Detection results | TF.js → Zustand store → BoundingBoxes overlay | On-device only |
| GPS coords | navigator.geolocation → formatCoords → display | On-device only |
| Device time | Date object → useLocalTime → TopRightPanel | On-device only |
| Battery | navigator.getBattery → hudStore | On-device only |
| Voice query | Web Speech API → /api/jarvis → Gemini → response | Transcript only (no GPS, no frames) |

## State Management — Zustand v5

// Zustand v5 changes the import: use import { create } from 'zustand' — not createStore

// hudStore.ts — simplified structure interface HUDState { detections: Detection[]; fps: number; battery: number; coords: { lat: number; lng: number } ¦ null; jarvisOpen: boolean; setDetections: (d: Detection[]) => void; setFPS: (f: number) => void; setBattery: (b: number) => void; setCoords: (c: { lat: number; lng: number } ¦ null) => void; toggleJarvis: () => void; }

# 04  PHASE-BY-PHASE BUILD PLAN

The project is divided into four phases across 13 weeks. Each phase has a clearly defined scope. Do not begin Phase N+1 work until Phase N deliverables are complete and the build is passing.

PHASE 1  Camera + Detection + HUD Shell  Weeks 1 – 3

The goal of Phase 1 is a working AR overlay on a real phone camera feed. By the end of Week 3, pointing the phone at any room should show real-time bounding boxes with COCO-SSD labels rendered over the live video.

## Week 1 — Project Bootstrap & Camera

- Scaffold Next.js 16.2.1 project with TypeScript, Tailwind v4, ESLint

- Configure app/globals.css with full @theme {} token set

- Load Orbitron and Share Tech Mono from Google Fonts in layout.tsx

- Implement CameraFeed.tsx — getUserMedia, permission gate UI, video ref

- Implement useCamera.ts hook with stream cleanup on unmount

- Create HUDShell.tsx — absolute-positioned overlay container on top of video

- Add Scanlines.tsx and AnimatedGrid.tsx visual overlays

- Add CornerBrackets.tsx reusable component

- Deploy skeleton to Vercel — confirm camera works on mobile Chrome

## Week 2 — TensorFlow.js Integration

- Install @tensorflow/tfjs and @tensorflow-models/coco-ssd

- Implement useDetection.ts — inference loop targeting 10+ FPS

- Lazy-load TF.js using dynamic(() => import(...), { ssr: false })

- Add FPS counter using requestAnimationFrame delta tracking

- Implement BoundingBoxes.tsx — SVG overlay with detection rectangles

- Style bounding box labels with Orbitron font, hud-cyan colour

- Initialise Zustand v5 hudStore with detections and fps slices

- Confirm COCO-SSD loads from CDN cache, not re-downloaded each session

## Week 3 — HUD Panels & Phase 1 Polish

- Implement TopLeftPanel.tsx — object count, FPS, scan status indicator

- Implement TopRightPanel.tsx — battery level, local time display

- Implement BottomBar.tsx — scrollable detected object list

- Implement useBattery.ts and useLocalTime.ts hooks

- Add animate-scan and animate-pulse-hud CSS keyframe animations

- Implement glitch effect animation on CORVUS wordmark

- Full mobile device test on Chrome Android — fix any layout issues

- npm run build must pass cleanly before Phase 2 begins

## Phase 1 Deliverables

| Deliverable | Acceptance Criteria | Priority |
| --- | --- | --- |
| Camera feed | Live getUserMedia on mobile Chrome | Required |
| Object detection | COCO-SSD ≥10 FPS on mid-range Android | Required |
| HUD overlay | All 3 panels + corner brackets | Required |
| Visual identity | Full cyan/dark aesthetic applied | Required |
| Vercel deployment | Live URL accessible on phone | Required |
| Build | npm run build passes cleanly | Required |

PHASE 2  Location, Device Sensors & Jarvis  Weeks 4 – 7

Phase 2 enriches the HUD with device sensor data and adds the Jarvis voice assistant overlay. All data remains on-device except voice transcripts sent to Gemini via the serverless proxy.

## Week 4 — GPS & Location Display

- Implement useLocation.ts using navigator.geolocation.watchPosition

- Debounce updates — only re-query after device moves > 50m

- Implement formatCoords() util — degrees/minutes/seconds display

- Display formatted coords in TopRightPanel (never raw decimals)

- Add heading display using DeviceOrientationEvent if available

- Implement fallback UI when geolocation is denied or unavailable

## Week 5 — Environmental Sensor Overlays

- Add device motion/acceleration data via DeviceMotionEvent

- Display compass bearing in HUD (alpha from DeviceOrientationEvent)

- Add network status indicator (navigator.onLine, connection.effectiveType)

- Battery drain rate estimation based on level delta over time

- Animate TopRightPanel data updates with Framer Motion v12

## Week 6 — Jarvis Voice Interface

- Implement /api/jarvis/route.ts — Next.js Route Handler

- Configure Gemini 2.0 Flash-Lite via @google/generative-ai SDK

- Build system prompt: inject object names, heading, battery, fps (no GPS)

- Implement Web Speech API voice input in BottomBar.tsx

- Add Jarvis response panel with typewriter animation effect

- Store Gemini API key in Vercel environment variables only

- Implement loading, error, and timeout states for all API calls

## Week 7 — Phase 2 Integration & Testing

- Integration test: all panels updating simultaneously without jank

- Measure FPS impact of new sensor hooks — must stay ≥10 FPS

- Test Jarvis on real device — latency, accuracy, error handling

- Add keyboard shortcut (J key) and tap gesture for Jarvis toggle

- Full Lighthouse audit — target ≥85 on mobile

- npm run build must pass before Phase 3

## Phase 2 Deliverables

| Deliverable | Acceptance Criteria | Priority |
| --- | --- | --- |
| GPS display | Formatted coords, debounced, no external API | Required |
| Compass bearing | Real-time from DeviceOrientationEvent | Required |
| Sensor overlays | Network, motion, battery drain rate | Required |
| Jarvis voice | Web Speech + Gemini via /api/jarvis | Required |
| Privacy maintained | No GPS in Gemini context, no frames sent | Required |
| Lighthouse | ≥85 on mobile | Target |

PHASE 3  Advanced Computer Vision  Weeks 8 – 10

Phase 3 adds MediaPipe-powered face detection, Tesseract OCR for text recognition, and Web Speech for ambient audio transcription. These are advanced features — do not begin until Phase 2 is stable.

## Week 8 — MediaPipe Face Detection

- Install @mediapipe/face_detection (lazy loaded, ssr: false)

- Add face count overlay to TopLeftPanel

- Display aggregate data only — count of faces, no biometric data stored

- Add anonymization option: blur bounding box content in face regions

- Test memory footprint with both COCO-SSD and MediaPipe active simultaneously

## Week 9 — Tesseract OCR

- Install tesseract.js (lazy loaded)

- Implement OCR mode toggle in BottomBar — off by default

- On activation, capture video frame to canvas and run OCR

- Display extracted text in a dedicated HUD panel overlay

- Rate-limit OCR — maximum once per 2 seconds to preserve battery

- Implement confidence threshold filter — only display text above 80%

## Week 10 — Speech Transcription & Phase 3 Polish

- Implement ambient speech transcription mode using Web Speech API

- Display live transcript in a scrolling HUD log panel

- Add per-feature toggle switches in a collapsible settings panel

- Memory audit: run with face detection + OCR + detection active

- Ensure JS heap stays below 300 MB with all features on

- npm run build must pass before Phase 4

## Phase 3 Deliverables

| Deliverable | Acceptance Criteria | Priority |
| --- | --- | --- |
| Face detection | MediaPipe, count only, no biometric storage | Required |
| OCR overlay | Tesseract, rate-limited, confidence filtered | Required |
| Speech transcript | Web Speech API, ambient mode | Required |
| Settings panel | Per-feature toggles, collapsible | Required |
| Memory constraint | Heap < 300 MB with all features active | Required |

PHASE 4  Performance, PWA & Launch  Weeks 11 – 13

Phase 4 is about polish, performance hardening, and making Corvus production-ready. The Web Worker offloads TF.js from the main thread entirely. The app becomes installable as a PWA.

## Week 11 — Web Worker Migration

- Create workers/detection.worker.ts

- Move all TF.js + COCO-SSD inference into the worker

- Use Comlink or raw postMessage to pass frame data and receive detections

- Benchmark FPS before and after — target measurable improvement

- Ensure worker terminates cleanly on component unmount

- Handle worker errors gracefully with fallback to main-thread inference

## Week 12 — PWA & Offline Support

- Add next-pwa or custom service worker via next.config.ts

- Cache COCO-SSD model weights in service worker cache (IndexedDB)

- Create manifest.json with Corvus branding, icons, theme colour

- Ensure app is installable on Android Chrome and iOS Safari

- Implement offline splash screen with graceful feature degradation

- Camera and detection must work 100% offline after first load

## Week 13 — Final Polish & Launch

- Full performance audit: FPS, heap, battery, Lighthouse

- Fix all ESLint warnings (errors already must be zero throughout)

- Add onboarding flow: permission requests, feature tour

- Test on 3 different Android devices + iOS Safari

- Write README with screenshots and live demo link

- Deploy final production build to Vercel

- LinkedIn launch post + portfolio update

## Phase 4 Deliverables

| Deliverable | Acceptance Criteria | Priority |
| --- | --- | --- |
| Web Worker | TF.js fully offloaded, main thread free | Required |
| PWA | Installable, model cached, offline capable | Required |
| Performance | All metrics at or below targets | Required |
| Lighthouse | ≥90 on mobile | Target |
| README | Screenshots, demo link, setup guide | Required |
| Live deployment | Vercel production URL, publicly accessible | Required |

# 05  MASTER TIMELINE

| Week | Phase | Focus | Milestone | Status |
| --- | --- | --- | --- | --- |
| Week 1 | Phase 1 | Camera feed, project scaffold, HUD shell | Vercel deploy (skeleton) | In progress |
| Week 2 | Phase 1 | TF.js + COCO-SSD integration, bounding boxes | Detection live on device | Planned |
| Week 3 | Phase 1 | All HUD panels, animations, mobile polish | Phase 1 MVP complete | Planned |
| Week 4 | Phase 2 | GPS + formatCoords, heading display | Location in HUD | Planned |
| Week 5 | Phase 2 | Device motion, network, battery rate | All sensor overlays live | Planned |
| Week 6 | Phase 2 | Jarvis: /api/jarvis, Gemini, voice input | Voice query working | Planned |
| Week 7 | Phase 2 | Integration testing, Lighthouse, Phase 2 close | Phase 2 complete | Planned |
| Week 8 | Phase 3 | MediaPipe face detection | Face count in HUD | Planned |
| Week 9 | Phase 3 | Tesseract OCR overlay | OCR mode working | Planned |
| Week 10 | Phase 3 | Speech transcript, settings panel, memory audit | Phase 3 complete | Planned |
| Week 11 | Phase 4 | Web Worker migration for TF.js | Main thread freed | Planned |
| Week 12 | Phase 4 | PWA, service worker, model caching | App installable | Planned |
| Week 13 | Phase 4 | Final polish, README, production deploy, launch | LAUNCH | Planned |

# 06  PRIVACY & SECURITY

Corvus is built on a zero-external-data principle. The camera feed, ML results, GPS coordinates, and all biometric data are processed entirely on the user's device and never transmitted externally.

## What Leaves the Device

| Data | Details |
| --- | --- |
| TF.js model weights | Downloaded from TF Hub on first load only. No user data attached. |
| Voice transcript | Sent to /api/jarvis (Vercel serverless) then to Gemini 2.0 Flash-Lite. Text only. No GPS, no frames, no images. |

## What Never Leaves the Device

- Raw camera frames — never stored, never transmitted

- GPS coordinates — formatted for display only, never sent to Gemini or any API

- Individual face data — count only, no biometric information

- OCR results — displayed in HUD, never logged externally

- Speech transcripts in ambient mode — local only

## Permanently Removed APIs

// These were in the original AGENTS.md and have been fully removed from Corvus

| Removed Service | Replacement / Reason |
| --- | --- |
| Nominatim / OpenStreetMap | Replaced by formatCoords() local helper |
| OpenWeatherMap | No weather data — time from device clock |
| OpenAQ | No air quality data |
| Wikipedia / landmark API | No POI enrichment |
| MongoDB Atlas | No session logging |
| Sentry | No error telemetry |
| Any analytics service | No tracking whatsoever |

## Security Rules

- Gemini API key lives in Vercel env vars only — never in client code

- No API key is ever exposed to the browser

- No CORS configuration that would allow external sites to call /api/jarvis

- All browser permission requests are gated behind explicit user gestures

# 07  PERFORMANCE CONSTRAINTS

All performance targets are measured on a mid-range Android device (e.g. Redmi Note 11, Samsung A53). Desktop performance is not the target baseline.

| Metric | Target | Tool | Check At |
| --- | --- | --- | --- |
| Metric | Target | Measured At | Enforcement |
| Initial load | < 5s on 3G | Lighthouse / DevTools | Phase 1 Week 3 |
| Model load | < 3s (cached) | console.time in useDetection | Phase 1 Week 2 |
| Detection FPS | ≥10 FPS | FPS counter in HUD | Every phase |
| JS heap | < 300 MB | Chrome DevTools Memory | Phase 3 Week 10 |
| Battery drain | < 10%/hr | Device battery log | Phase 2 Week 5 |
| Lighthouse | ≥85 | Lighthouse mobile audit | Phase 2 Week 7 |
| Lighthouse | ≥90 | Lighthouse mobile audit | Phase 4 Week 13 |

## Lazy Loading Strategy

- TensorFlow.js and COCO-SSD: never in the initial bundle

- MediaPipe (Phase 3): lazy loaded, ssr: false

- Tesseract.js (Phase 3): lazy loaded, ssr: false

- All ML components wrapped in dynamic(() => import(...), { ssr: false })

- Web Worker (Phase 4): further isolates TF.js from main thread

# 08  RISK REGISTER

| Risk | Likelihood | Impact | Mitigation | Area |
| --- | --- | --- | --- | --- |
| TF.js too slow on device | High | High | Web Worker in Phase 4; WebGL backend | Technical |
| iOS Safari camera access blocked | Medium | High | Test early W1; document iOS-specific workarounds | Platform |
| Framer Motion v12 breaking change | Medium | Medium | Review migration guide before use; pin version | Dependency |
| Zustand v5 API mismatch | Medium | Medium | Use create from 'zustand' not createStore | Dependency |
| Vercel cold start latency | Low | Medium | Edge runtime for /api/jarvis if needed | Infrastructure |
| Gemini API rate limit | Low | High | Debounce Jarvis calls; show loading state | External API |
| DeviceOrientation blocked (iOS) | High | Medium | Request permission via user gesture; graceful fallback | Platform |
| Heap bloat (multiple ML models) | Medium | High | Memory audit Phase 3; unload inactive models | Performance |

# 09  VISUAL IDENTITY

The Corvus visual system is built around a dark tactical HUD aesthetic. Every design decision reinforces the idea that the user is looking through a piece of sophisticated surveillance or reconnaissance equipment.

| Property | Specification |
| --- | --- |
| Primary colour | #00D4FF — hud-cyan |
| Background | #0A0A0F — hud-dark |
| Panel background | rgba(0, 212, 255, 0.05) |
| Border colour | rgba(0, 212, 255, 0.3) |
| Primary font | Orbitron — headings, labels, wordmark |
| Data font | Share Tech Mono — values, coordinates, FPS |
| Corner brackets | Present on all HUD panels — non-negotiable |
| Scanlines | CSS ::after pseudo-element on root |
| Border radius | Maximum rounded-sm — angular by design |
| Backgrounds | Dark only — no white, no light themes |

## Logo Guidance

The Corvus wordmark uses Orbitron Bold. The logo mark is a geometric raven/crow silhouette constructed from angular circuit-board-style line segments. The eye is a single glowing cyan dot (#00D4FF). The logo must read clearly at 24px height for favicon use.

# 10  DEPLOYMENT PLAN

## Hosting: Vercel Free Tier

- All phases deploy to Vercel via vercel --prod

- Preview deployments on every push to main

- Environment variable: GEMINI_API_KEY (set in Vercel dashboard, never committed)

- No paid add-ons, no Vercel Postgres, no Edge Config

## Deploy Checklist (Each Phase)

- npm run lint — zero errors

- npm run build — passes cleanly

- Test camera + detection on physical Android device

- Verify Vercel env vars are set in dashboard

- vercel --prod

- Open production URL on phone and verify core features

## Environment Variables

| Variable | Notes |
| --- | --- |
| GEMINI_API_KEY | Required for /api/jarvis. Set in Vercel dashboard. Never in .env.local that gets committed. |

# 11  AI AGENT RULES

This section is a quick-reference summary for AI coding agents (Claude Code, Cursor, Copilot). See AGENTS.md for the full canonical rules.

| Rule | Category |
| --- | --- |
| YES Add 'use client' to every browser-API component | Client vs Server |
| YES Wrap ML components in dynamic import, ssr: false | Performance |
| YES Add all tokens to @theme {} in globals.css | Tailwind v4 |
| YES Use named Tailwind tokens (bg-hud-cyan, etc.) | Visual Identity |
| YES Keep GPS out of all Gemini API calls | Privacy |
| NO Create tailwind.config.ts | Tailwind v4 |
| NO Use <form> elements | Next.js rules |
| NO Add paid APIs or services | Budget |
| NO Store camera frames or face biometrics | Privacy |
| NO Reintroduce any removed API | Privacy |
| NO Use inline styles instead of Tailwind tokens | Visual Identity |
| NO Begin next phase without passing build | Process |

CORVUS

Mobile AR Tactical HUD

Project CORVUS-01  ·  Author: Nirmal  ·  License: MIT  ·  Budget: ₹0